## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 5.1.2026. | Amina Gutošić | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Navigate to the Profile tab and note the current number of ratings. 8. Enter book name in search bar ("The Secret History"). 9. Click on the book and open the Book Details page. 10. Give a rating for the book by clicking on the stars (5 stars). 11. Remove the rating by clicking on the stars again. 12. The system displays a message: “Rating removed.” 13. Navigate back to the Profile tab. 14. Observe that the number of ratings has increased by 1, even though the rating was removed. EXPECTED RESULT: When the user removes a rating, the total number of ratings displayed on the Profile page should not increase. Link for the video: https://drive.google.com/file/d/19L_9YyzN-Dsafq3mDSagIxHDKQE-japR/view?usp=sharing | [6 empty] | New |  |  |  |  | New
2 | 7.1.2026. | Nejla Čajdin | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Enter book name in search bar ("The Secret History"). 8. Click on the book and open the Book Details page. 9. Check the publishing date (September 16, 1992). 10. Rate the book and click "Write a review". 11. Review tab is opened. 12. Select the reading dates for the review (Start date: October 16, 1952; End date: today). 13. Click "Post". 14. The review is published even though the reading start date is earlier than the book’s publishing date. EXPECTED RESULT: The system should not allow the user to submit a review with a reading start date earlier than the book’s publishing date. Link for the video: https://drive.google.com/file/d/1gNQ65eRaBpxPT5SyIeNxOURzRmiWanXp/view?usp=sharing | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 7.1.2026. | Hasna Bunar | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Enter book name in search bar ("The Secret History"). 8. Click on the book and open the Book Details page. 9. Rate the book and click "Write a review". 10. Review tab is opened. 11. Write the review and click "Post". 12. Navigate back to the Book Details Page and find your review. 13. In the section where your review is, under your profile picture, the review count is displayed as 0 reviews, even though one review exists. EXPECTED RESULT: After posting a review, the review count displayed under the user’s profile on the Book Details page should accurately reflect the actual number of reviews written by the user. Link for the picture: https://drive.google.com/file/d/1LcaLyi-b-VS8HjTjUR3U9htJ1GqeUkPd/view?usp=sharing | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 7.1.2026. | Amina Gutošić | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Click on the user's profile icon in navigation bar. 8. Dropdown is shown. 9. Select "Groups" from the dropdown. 10. User is successfully redirected to Groups page. 11. Click "create a group" clickable text. 12. "Create a Group" form is shown. 13. Fill the required fields with valid values. 14. Click "Create" button at the end of the form. 15. Error "1 error prohibited this group from being saved: Please try again later." is shown, even though all fields are valid. EXPECTED RESULT: After filling all fields with valid values, the group should be successfully created. Link for the video: https://drive.google.com/file/d/1-yTwyZcZrSW4hhprvZTlZ_-q4h4-J9a3/view?usp=sharing | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 7.1.2026. | Nejla Čajdin | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Click on the user's profile icon in navigation bar. 8. Dropdown is shown. 9. Select "Discussions" from the dropdown. 10. User is successfully redirected to Discussions page. 11. Click "start new topic" clickable text. 12. "Post a New Discussion Topic" form is shown. 13. Fill the required fields with valid values. 14. Click "Post" button at the end of the form. 15. Created discussion is shown, with message of success "Your topic was posted.". 16. Click on the user's profile icon in navigation bar. 17. Dropdown is shown. 18. Select "Discussions" from the dropdown. 19. User is successfully redirected to Discussions page. 20. Discussions page shows 0 topics, even though new topic was just created EXPECTED RESULT: Discussions page should show user's topics. Link for the video: https://drive.google.com/file/d/12wFpv9qqo_6Upq8c2GLQqUrZFYnDAxS7/view?usp=sharing | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | 7.1.2026. | Hasna Bunar | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Click on the „ My Books “ in header bar. 8. My Books page is shown. 9. In Bookshelves we see four categories (All, Want to Read, Currently Reading, Read). 10. Categories in Booshelves are not accurate EXPECTED RESULT: Number of books in Bookshelves Categories (All, Want to Read, Currently Reading, Read) must be accurate . Link for the photo-proof: https://drive.google.com/file/d/1-DaTBvc1j4WzaipoMKAVdQuGwlnPVGLB/view | [6 empty] | New | [6 empty] | Closing | Development
7 | 7.1.2026. | Amina Gutošić, Nejla Čajdin, Hasna Bunar | 1. Open the Google Chrome web browser. 2. Navigate to https://www.goodreads.com/user/sign_in. 3. Choose the way you want to sign in. 4. Enter valid credentials. 5. Click the "Sign in" button. 6. The system successfully logs in the user and redirects them to the Home Page. 7. Click on the user's profile icon in navigation bar. 8. Dropdown is shown. 9. Select "Profile" from the dropdown. 10. User is successfully redirected to Profile page. 11. Click on book that has been read .(Book must be rated by user) 12. Click „Write a review“ (under book photo and rating stars) 13. „Date started“ field allows user to enter reading year before users birthyear. EXPECTED RESULT: User is not able to „start reading“ before his birthyear. Link for the video: https://drive.google.com/file/d/1egiUpI8DO9PlFuC2qe3sIfHGteMVVbvz/view | [6 empty] | New | [7 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).